## Summary
Field | Details
Project Name | National Proficiency Scope Planning
Updated | 2026-07-20
Current Understanding | National Proficiency is a native mobile app (iOS + Android), account-required (no guest access), completely unrelated to Tactical Rabbi (no information crossover). It is a proficiency records-keeping platform across three pillars -- Medical, Firearms, Fitness -- administered by vetted Approved Instructors; National Proficiency itself takes no responsibility for the underlying qualification standards or outcomes (see Business Goal, R-002/R-003). User-side flow: branded launch animation -> account creation (basic info -> issued a unique serial number/code to access the account) or login -> individual profile page (photo, rank, medals, next-accomplishment guidance) -> tab bar with Home, Chat/Messaging, and Media, tier-gated (Free / Mid TBD / Premium). Instructor/backend side: Approved Instructors register and are vetted via a website (choosing a specialty -- Firearms, Fitness, or Medical), sign a waiver to follow National Proficiency's standards. CORRECTED registration flow: the student, not the instructor, now initiates a qualification registration from their own profile (picking category -- Medical/Firearms/Fitness); the app already knows their current tier and only allows registering for the next eligible one, then recommends nearby instructors (Google Calendar invite sent). Instructors access qualification standards on test day -- scoped only to what an active student registration requires, not a free browse of every tier -- record results (Shooter's Global shot timer or manual entry), and grade strictly pass/fail with a mandatory edit-audit-trail. An instructor can upgrade a student's tier on a Pass, but cannot lower/remove a tier directly -- only submit a downgrade request with a required reason. A zip-code-based locator map lets users find nearby instructors. Two cofounders sit above instructors with full access to edit any student or instructor record. Every user signs a liability waiver: National Proficiency is solely a records-keeping company, not responsible for shooting/medical/fitness outcomes -- that liability, and legal compliance, is the individual's own. Media tab also awards quiz-verified badges for watching specific training videos. A Home tab leaderboard for Fitness and Firearms (badges earned, fastest mile, longest distance, etc.) is fed in part by an optional Garmin/Apple Watch/Strava integration users can connect -- which the client also floated as a possible future basis for virtual, remote qualifications. The client also confirmed a full qualifications/training standards document exists and will be provided later, which should resolve the biggest remaining content gap (Q-002, Q-003, S-011) once received. New: registration (both students and instructors) will include third-party ID verification (e.g. ID.me) confirming the person is 18+ and, per the client, "legally allowed to own a firearm" -- without National Proficiency storing sensitive ID/legal documents itself. This also lets the system detect a banned person trying to re-register under new information. New content-visibility rules: Medical and Fitness qualification standards are fully public (each tops out at a ceiling level); Firearms exact drills stay confidential, but each tier publicly shows the general skills needed to prepare. New profile feature: a Pokemon-style progression visual showing earned tiers/medals in full color, the in-progress tier grayed out, and future tiers blacked-out/locked as a preview.
Business Goal | National Proficiency is a records-keeping/tracking company: it documents where people are qualifying (medical, firearms, fitness) and what they currently hold, via vetted Approved Instructors -- it does not set or guarantee the underlying training standards and assumes no liability for outcomes (client's own description). Exact target market/customer segment and monetization beyond the three membership tiers is still not stated -- see Q-001.
Highest Priority Next | Receive the client's qualifications/training standards document (Q-002, Q-003, S-011) once available. Resolve the ID-verification vendor scope urgently (Q-025, R-005) -- confirm whether the chosen vendor can actually verify firearm eligibility or only identity/age, since this is a real legal-exposure point. In parallel, resolve P0 items: account/auth rules including the serial number vs. login question (Q-005, Q-022), Mid-tier feature list and tier pricing (Q-009, Q-010), the raffle legal/compliance risk (R-001), instructor vetting criteria and downgrade-approval authority (Q-015, Q-021, Q-023), whether instructor registration/vetting is web or in-app (Q-019), and legal review/drafting of both waivers (S-016).
Verification Required | Client confirmation of navigation structure, monthly-challenge mechanics, Home-vs-Messaging community overlap and tier-gating (Q-004, Q-011), exact Media tab video categories (Q-008), the pre-registration approval workflow (Q-014), Google Calendar and Shooter's Global integration details (Q-016, Q-017), leaderboard metric list and Medical inclusion (S-021), wearable-platform data points (S-022), and locator-map search/filter scope (Q-024).
Open Decisions | Login mechanism, profile-page landing screen, tab order, account-required access, the three-tier structure, the three proficiency pillars, strict pass/fail grading, the edit-audit-trail requirement, the two-cofounder Owner role, instructor upgrade/no-unilateral-downgrade rule, and both required waivers are decided in direction -- see DECISIONS.md. Mid tier, all pricing, the full qualification standards content, and the actual waiver legal text remain undecided.
Proposal Notes | App concept, tier/paywall structure, instructor/qualification workflow, role hierarchy, and liability model now captured. Still not proposal-ready -- multiple P0 items open, plus legal/compliance risks (R-001 raffle, R-002/R-003 now partially mitigated by the liability waiver but still need enforceability review) that should be resolved before proposing pricing or timelines. See PROPOSAL_READINESS.md.
Note on A1: Column A = labels, Column B = details. Anything not yet confirmed by the client is left as TBD or flagged with the related Q-### question -- nothing here is guessed.

## Scope Items
ID | Source Plan | Priority | Area | Work Item | Current Status | Completed? | Completed Date | What Remains | Build Reference | Testing Reference
Q-001 | Client Kickoff Notes | P2 | Database / records | What is National Proficiency's target audience and business model? CONFIRMED: three proficiency pillars (Medical, Firearms, Fitness), tracked via vetted-instructor-administered pass/fail testing. CONFIRMED: separate brand from Tactical Rabbi, no crossover. CONFIRMED: business model is records-keeping only -- National Proficiency documents where people qualify and what they hold, and takes no liability for the underlying standards or outcomes (see S-016, R-002, R-003). | Waiting on Client | No |  | Only the specific target market/customer segment (e.g. general public, security professionals, a particular industry) and any monetization beyond the three membership tiers remain unstated -- not proposal-blocking on its own now that the core business model is confirmed. | Database / records | Client confirmation in writing (optional detail).
Q-002 | Client Kickoff Notes | P0 | Client portal | What are the specific ranks/levels in the progression system, and what are the criteria to advance from one to the next? Mechanism now confirmed: ranks are earned by passing instructor-administered qualifications (S-011, S-013). Client confirmed a full qualifications/training standards document exists and will be provided on a later date. | Waiting on Client | No |  | Full rank list and advancement rules per rank -- client has confirmed the source document exists and is forthcoming (see S-011); this row stays open until it's received and reviewed. | Client portal | Client-provided rank list (expected via the forthcoming standards document); QA against one test account per rank tier.
Q-003 | Client Kickoff Notes | P0 | Client portal | What are the specific medals/achievements available, and how is each one earned? Mechanism now confirmed: a medal/badge is awarded automatically when an instructor marks a qualification Pass (S-013). Client confirmed a full qualifications/training standards document exists and will be provided on a later date. | Waiting on Client | No |  | Full medal/achievement list and the qualification each one maps to -- expected via the forthcoming standards document (see S-011). | Client portal | Client-provided medal list and earn criteria.
Q-004 | Client Kickoff Notes | P1 | Client portal | Is the Home tab's 'community aspect' the same feature as the separate messaging/community tab, or two distinct features? If distinct, what belongs on Home vs. in Messaging? | Waiting on Client | No |  | Client clarification separating Home content from Messaging tab content. | Client portal / Notifications | Client confirmation; wireframe review.
Q-005 | Client Kickoff Notes | P0 | User management | How are accounts created -- self-registration, admin/organization-issued, or invite-only? Is a password-reset flow required? Is MFA required? | Waiting on Client | No |  | Account provisioning model, password-reset requirement, MFA requirement. | User management / Security / compliance | Client confirmation; acceptance criteria for login states.
Q-006 | Client Kickoff Notes | P1 | Client portal | How are monthly challenges created, tracked, and scored? Are there prizes or recognition tied to completion? | Waiting on Client | No |  | Challenge creation process, tracking/scoring rules, and any reward mechanics. | Client portal | Client-provided example of one full monthly challenge.
Q-007 | Client Kickoff Notes | P2 | Client portal | What is the full tab-bar/navigation structure? Confirmed so far: profile (post-login landing), Home, Chat/Messaging, Media. Any additional tabs (e.g. Settings, Notifications)? | Waiting on Client | No |  | Complete list and order of app tabs/navigation. | Client portal | Client-provided navigation map or wireframe.
Q-008 | Client Kickoff Notes | P1 | Client portal | What exactly are the 'firearms and building' videos on the Media tab? Two categories (firearms training + building/facility training) or one? Please confirm the exact wording/meaning -- this may also affect legal/compliance requirements for hosting the content. | Waiting on Client | No |  | Exact video category list and any hosting/compliance constraints per category. | Client portal (Media) / Security / compliance | Client confirmation of category list.
Q-009 | Client Kickoff Notes | P0 | Payments | What features belong to the Mid membership tier? Client indicated it is still being worked out. | Waiting on Client | No |  | Final Mid-tier feature list -- needed before tier-gating logic can be designed or built. | Payments / User management | Client-provided tier feature matrix.
Q-010 | Client Kickoff Notes | P0 | Payments | What is the price of each membership tier (Free/Mid/Premium), and what payment processor/billing system should be used (subscriptions, trials, upgrade/downgrade handling)? | Waiting on Client | No |  | Pricing per tier and billing platform decision -- needed to scope the Payments build area and for the proposal itself. | Payments | Client-provided pricing; confirmation of payment processor.
Q-011 | Client Kickoff Notes | P1 | Client portal | Monthly challenges are described as part of the Home tab (S-004), but the Free tier is described as not having access to challenges. Does that mean challenges appear on Home but are gated per-tier, or are challenges a separate screen outside Home? Also: is the Home 'community aspect' gated by tier, or available to all logged-in users including Free? | Waiting on Client | No |  | Clarify how tier-gating applies within the Home tab specifically. | Client portal / Payments | Client confirmation; wireframe review of Home tab per tier.
Q-012 | Client Kickoff Notes | P1 | Payments | How does the Premium-tier 'monthly raffle for challenges' work -- how are winners selected, what are the prizes, and who administers it? | Waiting on Client | No |  | Raffle mechanics and administration process. See related risk R-001 on legal/compliance exposure. | Payments / AI workflow | Client-provided raffle rules.
Q-013 | Client Kickoff Notes | P1 | Client portal | What does 'additional guidance based on things they're working on' (a Premium-tier perk) mean concretely -- human coach/trainer feedback, AI-generated recommendations, or something else, and how is it delivered in-app? | Waiting on Client | No |  | Definition of the guidance feature, who/what produces it, and delivery mechanism (in-app messages, notifications, reports, etc.). | Client portal / AI workflow | Client confirmation; one worked example.
R-001 | Client Kickoff Notes | P0 | Payments | Premium tier includes a monthly raffle tied to challenges. Paying for a subscription that includes a chance to win something can implicate sweepstakes/lottery/gambling law depending on jurisdiction. | Open | No |  | Legal/compliance review of the raffle mechanic before it is built or promoted -- may require an alternate no-purchase-necessary entry path or a redesign of the reward mechanic. | Security / compliance / Payments | Sign-off from client's legal counsel or compliance advisor.
R-002 | Client Kickoff Notes | P1 | Client portal | The Media tab hosts firearms training and medical training video content, which may carry liability, age-verification, or regulatory considerations depending on jurisdiction and audience. PARTIALLY MITIGATED: client confirmed every user signs a liability waiver stating National Proficiency is a records-keeping company only and bears no responsibility for shooting/medical/fitness outcomes (S-016) -- but a waiver's enforceability still needs legal confirmation, especially for firearms/medical content and any age-restricted material. | Open | No |  | Legal/compliance review of content liability, the waiver's actual enforceability in relevant jurisdictions, and any age/identity verification needed before granting Media tab access. | Security / compliance | Sign-off from client's legal counsel or compliance advisor.
S-001 | Client Kickoff Notes | P1 | Public form / Onboarding | Branded app launch animation ("National Proficiency") shown on open, before login. | Confirmed | No |  | Confirm animation length/style, brand assets (logo, colors, motion), whether it's skippable, and behavior on slow network/cold start. | Public form / Onboarding (mobile splash screen) | Client sign-off on animation mockup/video; QA of cold-start timing on iOS and Android.
S-002 | Client Kickoff Notes | P0 | User management | Account required for all app access -- no guest/anonymous use. New users create an account and select a membership tier; existing users log in. New users provide basic info and are then issued a unique serial number/code used to access their account (S-019). | Needs Clarification | No |  | Account provisioning method, password-reset flow, session/token expiration, MFA, error/lockout handling (Q-005); confirm tier selection happens at sign-up (S-007); clarify how the unique serial number (S-019) relates to login -- is it a replacement credential or an additional ID alongside a username/password (Q-022)? | User management / Security / compliance | Acceptance criteria for login success/failure states; client confirmation of provisioning method.
S-003 | Client Kickoff Notes | P0 | Client portal | Individual profile page: user photo, current rank, medals/achievements earned, guidance on the next accomplishment to pursue. | Needs Clarification | No |  | Earning mechanism now confirmed: rank/medals update automatically when an instructor marks a qualification Pass (S-013). Still needed: full rank/tier list, full medal/achievement list, logic/content for "what's next," and photo source -- see Q-002, Q-003. | Client portal / Database / records | Client confirmation of rank/medal list and progression rules; QA against a test account per rank.
S-004 | Client Kickoff Notes | P1 | Client portal | Home tab: updates feed, monthly challenges, a community aspect, and now also a Fitness/Firearms leaderboard (S-021). | Needs Clarification | No |  | Source/authorship of updates, monthly-challenge structure and progress tracking (Q-006), how 'community aspect' differs from the Messaging tab (Q-004) and from the new leaderboard (S-021), and how tier-gating applies within this single tab (Q-011). | Client portal / Notifications | Client confirmation of content types and one example monthly challenge; QA of feed rendering per role and per tier.
S-005 | Client Kickoff Notes | P1 | Client portal | Messaging / community communications tab, positioned second next to Home. Free tier is described as excluding chats; Premium tier includes them. | Needs Clarification | No |  | Whether this is 1:1 direct messaging, group/team chat, or a public feed; moderation rules; push notifications; media/attachment support (Q-004); confirm Mid-tier access level once defined (Q-009). | Client portal / Notifications | Client confirmation of message format and one example use case; QA send/receive across two test accounts per eligible tier.
S-006 | Client Kickoff Notes | P1 | Client portal (Media) | Media hosting tab (after Home and Chat), accessible only to premium subscribers: hosts medical training videos, fitness training videos, and firearms & building training videos. | Needs Clarification | No |  | Exact video category definitions (Q-008), video hosting/CDN/storage approach, who uploads content (admin only, presumably), streaming vs. download, captioning/accessibility, and any content liability/compliance review (R-002). | Client portal (Media) / Database / records | Client-provided sample video and category list; QA of playback and tier-gating (Premium-only access denied to Free/Mid test accounts).
S-007 | Client Kickoff Notes | P0 | Payments | Three membership tiers gate feature access. Free: app, profile page, Home page only -- no chats, media, or monthly challenges. Mid: feature set still being defined by the client. Premium: all features, plus monthly raffles tied to challenges, media access, chats, and additional personalized guidance. | Needs Clarification | No |  | Full Mid-tier feature list (Q-009), pricing per tier and billing platform (Q-010), upgrade/downgrade flow, and legal review of the raffle mechanic (R-001). This gates the build of nearly every other feature via entitlement/paywall logic. | Payments / User management | Client-provided tier feature matrix and pricing; QA of access boundaries per tier using one test account per tier.
Q-014 | Client Kickoff Notes | P1 | Admin dashboard | When a pre-registration is submitted, does it require a separate approval step by someone else, or does "approval information" just mean an automatic confirmation is generated and sent to the student? Please clarify the approval workflow. | Waiting on Client | No |  | Clear description of the approval step(s), if any, between submission and a confirmed registration. | Admin dashboard | Client confirmation.
Q-015 | Client Kickoff Notes | P1 | User management | How are instructors granted "Approved Instructor" status, and is certification per-category (e.g. an instructor certified for Firearms only couldn't administer Medical or Fitness qualifications)? | Waiting on Client | No |  | Instructor approval/designation process and whether category-specific certification applies. | User management | Client confirmation.
Q-016 | Client Kickoff Notes | P1 | External integration | What does the Google Calendar integration require in practice -- the student's personal Google Calendar (needing their OAuth consent), a shared/organizational calendar, or something else? What happens if the student has no Google account? | Waiting on Client | No |  | Confirmed calendar integration approach and no-Google-account fallback. | External integration | Client confirmation.
Q-017 | Client Kickoff Notes | P1 | External integration | Is "Shooter's Global" a confirmed technical/partner integration, and what interface does it expose for the app to receive shot-timer results (API, Bluetooth, file import, etc.)? | Waiting on Client | No |  | Confirmation of partner status and technical integration details, or confirmation this is a future/aspirational integration. | External integration | Client confirmation; technical documentation from Shooter's Global if a partnership exists.
Q-018 | Client Kickoff Notes | P2 | Admin dashboard | Is there a retest or appeal policy after a student fails a qualification (e.g. how soon can they re-register, is there a cap on attempts)? | Waiting on Client | No |  | Retest/appeal policy, if any. | Admin dashboard | Client confirmation.
R-003 | Client Kickoff Notes | P1 | Security / compliance | Qualification records (especially firearms and medical) likely carry legal/compliance requirements around record retention, access control, and edit chain-of-custody -- reinforced by the client's explicit request for an audit trail on edits. PARTIALLY MITIGATED: client confirmed the business model is explicitly records-keeping only, with a signed user waiver disclaiming responsibility for outcomes (S-016) -- still need legal confirmation this framing holds up, plus the retention/access rules themselves. | Open | No |  | Legal/compliance review of qualification record-keeping requirements: retention period, who can access records (cofounders have full access per S-014 -- confirm that's the intended access model), and whether the audit-trail format meets any applicable regulatory standard. Related to R-001, R-002. | Security / compliance | Sign-off from client's legal counsel or compliance advisor.
S-008 | Client Kickoff Notes | P0 | Admin dashboard | Approved Instructor role: same profile and access to all regular-user features/pages, plus instructor-only qualification-administration tools. CORRECTED: the original "+" button pre-registration entry point has moved to the student's profile -- see S-025. | Needs Clarification | No |  | How instructors are designated/approved, whether certification is per-category, and how instructor-only tools stay hidden from non-instructor users -- see Q-015. Registration is now initiated by the student (S-025), not the instructor. | Admin dashboard / User management | Client confirmation of instructor designation process; QA that instructor-only tools are hidden from non-instructor accounts.
S-009 | Client Kickoff Notes | P0 | Admin dashboard | SUPERSEDED: instructor manually pre-registers a student by typing in their info, category, tier, and date via a "+" button. | Removed | No |  | Client corrected this flow: registration is now student-initiated from their own profile, not instructor-initiated. Superseded by S-025 -- kept here, marked Removed, so the correction is traceable rather than silently overwritten. | Admin dashboard / Database / records | See S-025.
S-010 | Client Kickoff Notes | P1 | External integration | Google Calendar integration: on submission, sends the qualification date to the student so they know it's recorded and scheduled. | Needs Clarification | No |  | Whether this targets the student's personal Google Calendar or an organizational calendar, behavior with no Google account, time zone handling, and updates on reschedule/cancellation -- see Q-016. | External integration | Client confirmation of calendar integration approach; QA of invite delivery and reschedule/cancel sync.
S-011 | Client Kickoff Notes | P0 | Admin dashboard | Qualification standards library: on the day of testing, the instructor has access to that tier's qualification standard/course of fire to follow while administering the test. Client confirmed a full qualifications/training document covering all standards exists and will be provided later. NEW visibility rule per category: Medical and Fitness standards are fully PUBLIC (visible to everyone) since each tops out at a defined ceiling level. Firearms standards are CONFIDENTIAL -- the exact drills are hidden -- but each tier publicly shows the general skills needed to prepare, without revealing the exact test content. An instructor's access to standards content is scoped to what a specific active student registration requires (S-026), not an open browse of every tier. | Waiting on Client | No |  | Waiting on the client's full qualifications/training document (confirmed to exist, no date given). Once received: format as a structured checklist per category x tier; separate the public Medical/Fitness content from the confidential Firearms content plus its public "skills needed" summary per tier; confirm who maintains/updates standards over time. | Admin dashboard / Database / records | Client to provide the full qualifications/training document; QA that the correct standard loads for the selected category/tier once content is built from it.
S-012 | Client Kickoff Notes | P1 | External integration | Shot timer integration ("Shooter's Global"): shot-timer drill times can be recorded directly into the app during a firearms qualification. | Needs Clarification | No |  | Whether Shooter's Global is a confirmed technical/partner integration and what interface it exposes, what data is captured per drill, and fallback behavior if unavailable -- see Q-017. | External integration | Client confirmation of integration method/partner status; QA of a recorded drill time populating correctly, and of the manual-entry fallback.
S-013 | Client Kickoff Notes | P0 | Admin dashboard | Qualification grading: instructor checks off each individual qualification criterion (manual notes supported) and grades strictly pass/fail -- no partial/leniency. Any edit to recorded results is logged with an audit trail. On Pass, the student's profile automatically updates with the new medal/badge/accomplishment (tier upgrade). An instructor cannot lower/remove a student's tier directly -- they can only submit a downgrade request with a required reason (S-018). | Needs Clarification | No |  | Exact checklist criteria per category/tier (ties to S-011, Q-002, Q-003), audit-trail format (who/when/what changed, and whether it's visible to the student), retest/appeal policy after a Fail -- see Q-018. Directly updates the profile page built in S-003. | Admin dashboard / Database / records / Security / compliance | Client confirmation of the pass/fail checklist for one example qualification; QA that an edit after submission creates a visible audit entry; QA that a Pass updates the student's profile rank/medal.
Q-019 | Client Kickoff Notes | P1 | Admin dashboard | Is the instructor registration/vetting process a separate website build, or done within the mobile app? Client originally said instructors "register on the website," then later said the approval process "could be done on the app for vetting" -- these two statements haven't been reconciled yet. | Waiting on Client | No |  | Confirmation of whether a separate web application needs to be scoped and built, or whether instructor registration and vetting/approval both happen inside the mobile app (which would remove a whole extra build surface). | Admin dashboard | Client confirmation.
Q-020 | Client Kickoff Notes | P2 | User management | Can an instructor register/get approved for more than one specialty category (Firearms, Fitness, Medical), or only one per instructor? | Waiting on Client | No |  | Confirmation of single vs. multi-category instructor certification. | User management | Client confirmation.
Q-021 | Client Kickoff Notes | P0 | Admin dashboard | Who approves an instructor's tier-downgrade request -- the two cofounders specifically, or another review process? What happens if the request is denied, and is the student notified either way? | Waiting on Client | No |  | Confirmed approval authority and notification behavior for downgrade requests. | Admin dashboard / Security / compliance | Client confirmation.
Q-022 | Client Kickoff Notes | P0 | User management | Is the unique serial number/code issued at account creation a replacement login credential, or an additional ID used alongside a username/password (S-002)? How is it delivered, and can it be recovered or reset if lost? | Waiting on Client | No |  | Clear definition of the serial number/code's role in authentication, delivery method, and recovery process. | User management / Security / compliance | Client confirmation; acceptance criteria for account access using the code.
Q-023 | Client Kickoff Notes | P0 | User management | What are the specific vetting criteria and process for approving an instructor (e.g. background check, certification proof, references), and who conducts the vetting? | Waiting on Client | No |  | Documented vetting process and criteria per specialty category. | User management / Security / compliance | Client-provided vetting checklist or process description.
Q-024 | Client Kickoff Notes | P2 | Client portal | For the zip-code-based instructor locator map: what can a user search/filter by (category, specific drill/qualification, distance, availability), and is this feature available to all membership tiers, including Free? | Waiting on Client | No |  | Confirmed search/filter fields and tier availability for the locator map. | Client portal / External integration | Client confirmation; wireframe review.
F-001 | Client Kickoff Notes | P3 | Client portal (Media) | Beyond regular qualification medals, additional leaderboard-style badges people can earn or compete for to rank higher than peers, to build camaraderie. | Removed | No |  | Superseded by S-021 -- client provided concrete leaderboard details (Home tab, Fitness/Firearms, specific metrics) in a later message, elevating this from a tentative future idea to a scoped item. | Client portal (Media) / Reporting | See S-021.
S-014 | Client Kickoff Notes | P0 | Admin dashboard | Cofounder / Owner role: the two highest-level users (the app's cofounders) have access to all instructor and student files/records and can edit any individual part they see fit. | Needs Clarification | No |  | How this maps to system permissions (a distinct "Owner" role vs. broader "Admin"), whether cofounder edits are also logged in an audit trail (consistent with S-013's requirement), and whether cofounders are the approval authority for instructor downgrade requests (Q-021). | Admin dashboard / Security / compliance | Client confirmation of the permission model; QA that only the two designated cofounder accounts have full-record edit access.
S-015 | Client Kickoff Notes | P0 | Admin dashboard | Instructor registration & vetting: prospective instructors register, choose a specialty (Firearms, Fitness, or Medical), and are individually vetted before being listed as an Approved Instructor. Client has since said the vetting/approval step could be done within the app itself. Registration also includes third-party ID verification (S-023). | Needs Clarification | No |  | Whether registration and vetting are a separate website build or fully in-app (Q-019 -- client's two statements on this haven't been reconciled), the specific vetting criteria/process and who conducts it (Q-023), whether multi-category certification is allowed (Q-020), and how ID verification (S-023) sequences with vetting. | Admin dashboard / User management / Public form | Client-provided vetting checklist; QA of the full registration-to-approval flow for one test instructor.
S-016 | Client Kickoff Notes | P0 | Security / compliance | Two required waivers: (1) instructors sign a waiver agreeing to follow National Proficiency's standards; (2) every user signs a liability waiver acknowledging National Proficiency is solely a records-keeping company, takes no responsibility for shooting/medical/fitness qualification standards or outcomes, and that all liability -- including compliance with local, state, and federal law -- rests with the individual. | Needs Clarification | No |  | Actual waiver legal text (needs to come from the client's legal counsel), e-signature mechanism and storage, versioning if waiver text changes, and confirmation that waiver acceptance gates account/instructor activation. Directly relates to and partially mitigates R-002, R-003 -- but enforceability still needs a legal review. | Security / compliance / User management | Sign-off from client's legal counsel on waiver text; QA that an account/instructor cannot be activated without a recorded signature.
S-017 | Client Kickoff Notes | P1 | Client portal | Instructor locator map: a person can search by zip code to find the nearest approved instructors for the specific drills/qualifications they need. Related to the newer auto-recommendation flow in S-025 -- unclear whether this standalone map still exists separately or is now just how recommended instructors are displayed after registering (see Q-031). | Needs Clarification | No |  | Search/filter scope (category, specific drill, distance, availability) and tier availability -- see Q-024. Needs a mapping API integration. Confirm relationship to S-025's automatic instructor recommendation on registration -- Q-031. | Client portal / External integration | Client confirmation of search/filter fields; QA of search results against a set of test instructor locations.
S-018 | Client Kickoff Notes | P0 | Admin dashboard | Tier upgrade / downgrade-request workflow: an instructor can upgrade a student's tier directly upon completing a qualification (via the S-013 Pass flow), but cannot lower or remove a tier directly -- they can only submit a downgrade request, providing a required reason. | Needs Clarification | No |  | Who approves a downgrade request and what happens if it's denied (Q-021); whether the student is notified when a request is filed and/or resolved; whether supporting evidence beyond a text reason is required. | Admin dashboard / Security / compliance | Client confirmation of the approval workflow; QA that an instructor account cannot directly lower a tier, only submit a request.
S-019 | Client Kickoff Notes | P0 | User management | New account creation: an unregistered person creates an account with basic information, after which they are issued a unique serial number/code, specific to them, used to access their account. Registration also includes third-party ID verification (S-023). | Needs Clarification | No |  | Whether this serial number/code replaces or supplements username/password login (S-002), exact "basic information" fields required, delivery method, recovery process if lost (Q-022), and how this step sequences with ID verification (S-023). | User management / Security / compliance | Client confirmation of the full sign-up field list and how the code is delivered/used; QA of account access using the issued code.
S-020 | Client Kickoff Notes | P1 | Client portal (Media) | Video-completion badges: users can earn a digital badge for a specific Media tab video by passing an online quiz/test showing they paid attention to the content (e.g. a "How to Build an AR-15" video with a quiz, earning a badge on their profile). | Needs Clarification | No |  | Quiz content/format per video, pass threshold, retake policy, and how many videos need this treatment -- builds on the Media tab (S-006). | Client portal (Media) / Database / records | Client-provided example quiz for one video; QA that passing the quiz awards the badge on the profile page.
S-021 | Client Kickoff Notes | P1 | Client portal | Home tab leaderboard for Fitness and Firearms: ranks users by badges earned, fastest mile, longest distance, and other similar metrics. | Needs Clarification | No |  | Whether Medical is intentionally excluded from the leaderboard (client mentioned only Fitness and Firearms) or just not yet described; the full list of tracked metrics beyond badge count/fastest mile/longest distance; whether metrics come from wearable integrations (S-022) or instructor-recorded qualification data; opt-out/privacy for appearing on the leaderboard; tie-breaking rules; relationship to the Home tab's community aspect (S-004, Q-004, Q-011). Supersedes F-001, which described this idea tentatively before these details were given. | Client portal / Reporting | Client confirmation of exact metrics and category inclusion; QA that leaderboard rankings update correctly when a test account's stats change.
S-022 | Client Kickoff Notes | P1 | External integration | Wearable/fitness-platform integration: users can connect a Garmin, Apple Watch, or Strava account (their choice) to sync personal fitness/activity data into the app. | Needs Clarification | No |  | Which specific data points are pulled from each platform, how this feeds the leaderboard (S-021) and profile, OAuth/authentication per platform, fallback for users who don't connect a platform, and data-privacy/consent for syncing health/fitness data. | External integration / Client portal | Client confirmation of exact data points needed per platform; QA of a successful sync from at least one platform populating the leaderboard/profile correctly.
F-002 | Client Kickoff Notes | P3 | Admin dashboard | Future idea (client's own framing -- "could also be used later"): allow certain qualifications to be completed virtually/remotely using wearable-sourced performance data (S-022) tied to specific events, instead of in-person instructor administration. | Future Phase | No |  | Which qualifications (if any) would be eligible for virtual completion, how "specific events" are defined/administered without an instructor present, and anti-fraud/verification safeguards -- see risk R-004. Not proposal-blocking now per the client's own "later date" framing. | Admin dashboard / External integration | Client confirmation of scope/timing before any design work.
Q-025 | Client Kickoff Notes | P0 | Security / compliance | Which specific third-party ID-verification vendor will be used (client mentioned "ID.me" or similar)? Has it been confirmed that this vendor can verify someone is "legally allowed to own a firearm" -- that determination typically requires a NICS-style background check, distinct from standard identity/age verification, which is what services like ID.me normally provide. | Waiting on Client | No |  | Vendor selection and confirmation of exactly what it verifies (identity + age only, vs. actual firearm-purchase eligibility). See related risk R-005. | Security / compliance / External integration | Client confirmation; vendor documentation review.
Q-026 | Client Kickoff Notes | P1 | Security / compliance | What is the ban process -- who decides to ban a user (the cofounders, per S-014?), what are grounds for a ban, and is there an appeal process? | Waiting on Client | No |  | Documented ban criteria, authority, and appeal process, if any. | Security / compliance / Admin dashboard | Client confirmation.
Q-027 | Client Kickoff Notes | P1 | Security / compliance | If ID verification fails, or a person lacks eligible documentation, are they blocked from the app entirely, or only from firearms-related features (with Medical/Fitness still accessible)? | Waiting on Client | No |  | Confirmed behavior for a failed or incomplete verification. | Security / compliance / User management | Client confirmation; acceptance criteria for a failed-verification account state.
Q-028 | Client Kickoff Notes | P2 | Payments | Does the per-verification cost charged by the ID-verification vendor affect tier pricing or the overall business model (see Q-010)? | Waiting on Client | No |  | Confirmation of whether vendor fees are a pricing input. | Payments / External integration | Client confirmation; vendor pricing sheet.
R-005 | Client Kickoff Notes | P0 | Security / compliance | "Legally allowed to own a firearm" is a specific legal determination that typically requires a NICS-style background check -- standard ID-verification vendors (e.g. ID.me) generally verify identity and age, not firearm-purchase eligibility. Treating an identity-verification pass as confirmation of firearm eligibility could create a false sense of legal compliance and real liability exposure for National Proficiency, distinct from the liability the user waiver (S-016) covers, since this would be National Proficiency's own verification claim. | Open | No |  | Legal/compliance review of what verification is actually achievable and required, and whether the chosen vendor's service (Q-025) covers it or a separate/additional check is needed. Related to R-002, R-003. | Security / compliance / External integration | Sign-off from client's legal counsel; written confirmation from the ID-verification vendor of exactly what their product certifies.
Q-029 | Client Kickoff Notes | P1 | Security / compliance | Client described an instructor-visibility boundary tied to the instructor's own achieved level, but the exact wording was unclear (possible transcription issue): is an instructor ever able to view qualification standards above what a specific student's active registration requires -- e.g. for their own reference -- or is their access strictly limited to exactly what that one registration calls for? | Waiting on Client | No |  | Precise definition of the instructor access-boundary rule beyond "scoped to the active registration" (S-026). | Security / compliance | Client confirmation in writing to resolve the unclear phrasing.
Q-030 | Client Kickoff Notes | P2 | Client portal | For the profile's rank/medal progression visual (S-028): how many future tiers ahead should be visible-but-locked (just the next one, or all remaining), and is this one combined view or a separate view per category (Medical / Firearms / Fitness)? | Waiting on Client | No |  | Confirmed scope of the locked-preview tiers and whether the visual is per-category or combined. | Client portal | Client confirmation; wireframe review.
Q-031 | Client Kickoff Notes | P1 | Client portal | Does the new automatic instructor-recommendation-on-registration (S-025) replace the standalone zip-code instructor locator map (S-017), or do both exist as separate features? | Waiting on Client | No |  | Confirmation of whether S-017 remains a general browse/search map, in addition to S-025's recommendation step during registration, or whether one supersedes the other. | Client portal | Client confirmation.
S-025 | Client Kickoff Notes | P0 | Client portal | Student-initiated qualification registration (corrected flow): from their own profile, a student selects "Register"/"Choose qualification day," picks a category (Medical, Firearms, or Fitness), and the app -- already knowing their current tier from their profile -- only lets them register for their next eligible tier (no skipping ahead). Based on category, tier, and location, the student is recommended nearby instructors to choose from. Supersedes the earlier instructor-initiated flow (S-009, now Removed). | Needs Clarification | No |  | Full field list and flow details (date selection, approval step -- Q-014), how the recommendation engine ranks/filters instructors (ties to S-017 locator map -- Q-031), and confirmation this fully replaces instructor-side manual entry. | Client portal / Database / records / External integration | Client confirmation of the full corrected flow end to end; QA that a test student account can only select their next eligible tier, never a higher one.
S-026 | Client Kickoff Notes | P0 | Security / compliance | Scoped instructor access to qualification standards: an instructor cannot browse qualification data for tiers generally (e.g. "scroll through tier ten") -- they can only see the standard content relevant to the specific course a specific student is actively registered for. | Needs Clarification | No |  | Exact access-control implementation (per-registration grant, expiring after the qualification is graded?), and the unclear boundary condition raised in Q-029. | Security / compliance / Admin dashboard | Client confirmation of the access rule; QA that an instructor account cannot view standards content for a tier with no active matching student registration.
S-028 | Client Kickoff Notes | P1 | Client portal | Profile rank/medal progression visual ("skill tree"): shows earned tiers/medals in full color, the in-progress tier (medals still needed to advance) grayed out, and future tiers beyond that blacked-out/locked as a preview -- visible but not selectable or viewable in detail. | Needs Clarification | No |  | How many future tiers are shown locked, and whether this is one combined view or per-category (Q-030); ties directly to S-003 and to the confirmed per-tier content-visibility rules in S-011. | Client portal / Database / records | Client confirmation/wireframe review of the visual; QA against test accounts at different progress states (earned / in-progress / locked).
S-023 | Client Kickoff Notes | P0 | Security / compliance | ID verification during registration (students and instructors): a third-party service (client mentioned "ID.me" or similar) verifies the person is over 18 and, per the client, "legally allowed to own a firearm," without National Proficiency storing sensitive ID/legal documents on its own systems. | Needs Clarification | No |  | Vendor selection and confirmation of what it actually verifies (Q-025 -- age/identity vs. actual firearm eligibility, which is a distinct legal question, see R-005); what happens on failed verification (Q-027); data-flow confirmation that only a verification result/token is stored, never raw ID documents; consent/privacy disclosures; whether this applies to all tiers. | Security / compliance / External integration / User management | Client/legal confirmation of vendor and verification scope; QA that a test registration stores no raw ID document data, only a pass/fail verification result.
S-024 | Client Kickoff Notes | P0 | Security / compliance | Ban enforcement via identity verification: if a user is banned, the system uses their verified identity (from S-023) to detect and prevent them from re-registering under new account information. | Needs Clarification | No |  | Ban criteria and approval authority (Q-026); how a match against a banned identity is detected and handled (auto-block vs. flagged for review); whether an appeal process exists; whether this applies to both instructors and students. | Security / compliance / User management | Client confirmation of the ban process; QA that a banned test identity attempting to re-register with different account details is correctly detected and blocked.
R-004 | Client Kickoff Notes | P2 | Security / compliance | Virtual/remote qualifications sourced from wearable or fitness-tracker data (F-002) could be vulnerable to falsification -- e.g. GPS spoofing, another person wearing the device, or manipulated app data -- since a qualification is an official pass/fail record. | Open | No |  | Anti-fraud/verification safeguards to define before F-002 moves past future-phase status (e.g. live verification, cross-checked timestamps/location, or restricting virtual completion to lower-stakes categories only). Tied to F-002; lower urgency than R-001/R-002/R-003 since the underlying feature is explicitly future-phase. | Security / compliance / External integration | Legal/compliance and product review before F-002 is scoped for build.
Note on A1: ID prefixes: S-### scope items, Q-### open questions, R-### risks, F-### future ideas. Priority: P0 proposal blocker, P1 first version, P2 can wait, P3 future/optional.

## Ready for Review
ID | Feature / Workflow | Area | Status | Roles To Test | Test Steps | Expected Result | Data / Setup Needed | Automation / Manual Target | Build Reference | Date Added | Tester Return / Evidence Required
QA-001 (EXAMPLE) | Example: Client submits a public intake form | Public form | Needs Clarification | Public / anonymous user | Example: 1) Open form 2) Fill required fields 3) Submit | Example: Submission is saved and a confirmation is shown | Example: Sample form data | Manual | Public form | 2026-07-20 | Example: Screenshot of confirmation screen
Note on A1: IDs use QA-### internally; describe this tab to the client as review-ready items. No items are clear enough for review yet -- row 2 stays an EXAMPLE (italic gray) until a real item qualifies.

## System Capability Map
ID | Area | Capability / Workflow | Who Can Use It | How To Get There | Cypress Coverage / Command | Cypress Closure Status | Manual / Live QA Still Needed | Related QA Rows | Notes / Scope Expansion
CAP-001 | Public form / Onboarding | App launch -> branded animation | All users (pre-login) | Open the app on iOS or Android | Not built yet | Open | Confirm animation assets and timing once designed. |  | Relates to S-001.
CAP-002 | User management | Account creation / login (account required for all access) | New and returning users | App launch -> login/sign-up screen | Not built yet | Needs Clarification | Confirm account provisioning, password-reset flow, and tier selection at sign-up (Q-005, S-007). |  | Relates to S-002, S-007.
CAP-003 | Client portal | Individual profile page (photo, rank, medals, next steps) | Logged-in member (own profile), all tiers | Login -> lands on profile page | Not built yet | Needs Clarification | Confirm rank and medal system (Q-002, Q-003). |  | Relates to S-003. Landing page immediately after login.
CAP-004 | Client portal | Home tab (updates, monthly challenges, community) | Logged-in member, all tiers (challenges may be Premium/Mid only) | Tab bar -> Home | Not built yet | Needs Clarification | Confirm content sources, challenge structure, and per-tier gating within Home (Q-004, Q-006, Q-011). |  | Relates to S-004.
CAP-005 | Client portal | Messaging / community communications | Premium tier confirmed; Free tier excluded; Mid tier TBD | Tab bar -> Chat tab, next to Home | Not built yet | Needs Clarification | Confirm messaging model (Q-004) and Mid-tier access (Q-009). |  | Relates to S-005.
CAP-006 | Client portal (Media) | Media hosting -- medical, fitness, and firearms/building training videos | Premium tier only; Free and Mid excluded (Mid TBD) | Tab bar -> Media tab | Not built yet | Needs Clarification | Confirm video categories (Q-008), hosting approach, and content liability review (R-002). |  | Relates to S-006. New tab added after Home and Chat.
CAP-007 | Client portal | Student-initiated qualification registration (CORRECTED -- was instructor-initiated) | Students, from their own profile | Profile -> "Register"/"Choose qualification day" -> pick category -> app restricts to next eligible tier -> recommended instructors shown -> submit | Not built yet | Needs Clarification | Confirm approval workflow (Q-014), full form fields, and Google Calendar integration approach (Q-016). Corrected from an earlier instructor-initiated design -- see S-025, S-009 (Removed). |  | Relates to S-025, S-010. Supersedes the original instructor-"+"-button version of this row's description.
CAP-008 | Admin dashboard | Qualification administration & grading (course of fire, shot timer / manual entry, pass-fail checklist, audit trail) | Approved Instructors only | Open a registered qualification on test day -> standard/checklist -> record results -> Pass/Fail | Not built yet | Needs Clarification | Confirm qualification standards content (Q-002, Q-003), Shooter's Global integration (Q-017), and retest policy (Q-018). |  | Relates to S-011, S-012, S-013. A Pass updates the student's profile (S-003).
CAP-009 | Admin dashboard | Owner-level record access & edit (full instructor and student files) | Two cofounders only | Owner/admin console (details TBD) | Not built yet | Needs Clarification | Confirm this is a distinct permission tier from Admin generally, and whether cofounder edits are also audit-logged like instructor edits (S-013). |  | Relates to S-014.
CAP-010 | Admin dashboard | Instructor registration & vetting | Prospective instructors (pre-approval) | External registration website (Q-019) -> choose specialty -> vetting -> waiver -> Approved Instructor status | Not built yet | Needs Clarification | Confirm whether this is a separate web build (Q-019), vetting criteria (Q-023), and multi-category eligibility (Q-020). |  | Relates to S-015, S-016.
CAP-011 | Client portal | Instructor locator map (zip code search) | All users (tier TBD) | Location TBD in nav -- search by zip code | Not built yet | Needs Clarification | Confirm search/filter scope and tier availability (Q-024). |  | Relates to S-017.
CAP-012 | Client portal (Media) | Video-completion badge (watch + quiz) | Premium tier (Media tab access) | Media tab -> watch video -> take quiz -> badge awarded on profile | Not built yet | Needs Clarification | Confirm quiz content/format and pass threshold per video (see S-020). |  | Relates to S-020. Distinct from qualification-based medals (S-013).
CAP-013 | Client portal | Home tab leaderboard (Fitness & Firearms) | Logged-in members (tier availability TBD) | Tab bar -> Home -> leaderboard section | Not built yet | Needs Clarification | Confirm full metric list, Medical inclusion/exclusion, and data source (S-022) -- see S-021. |  | Relates to S-021. Supersedes F-001.
CAP-014 | External integration | Wearable/fitness-platform connection (Garmin, Apple Watch, Strava) | Logged-in members who opt in | Profile or settings -> connect account -> platform OAuth | Not built yet | Needs Clarification | Confirm data points per platform and consent/privacy handling -- see S-022. |  | Relates to S-022. Feeds S-021 leaderboard; may feed future virtual qualifications (F-002).
CAP-015 | Security / compliance | ID verification during registration (age 18+ and firearm eligibility) | All new registrants -- students and instructors | Registration flow -> third-party ID verification step -> pass/fail result | Not built yet | Needs Clarification | Confirm vendor and exact verification scope (Q-025); confirm no raw ID documents are stored (R-005). |  | Relates to S-023.
CAP-016 | Security / compliance | Ban enforcement / re-registration block | Cofounders (issue bans); system (auto-detect on new registration) | A banned identity attempts to re-register -> system matches against verified identity -> blocked or flagged | Not built yet | Needs Clarification | Confirm ban criteria, approval authority, and appeal process (Q-026). |  | Relates to S-024.
CAP-017 | Security / compliance | Scoped instructor access to qualification standards | Approved Instructors, limited to actively-registered students | Instructor opens a student's active registration -> sees only that course's standard, not other tiers | Not built yet | Needs Clarification | Confirm exact access-control mechanics and the unclear boundary raised in Q-029. |  | Relates to S-026, S-011.
CAP-018 | Client portal | Profile rank/medal progression visual ("skill tree") | All users, viewing their own profile | Profile page -> progression view | Not built yet | Needs Clarification | Confirm how many locked future tiers are shown and per-category vs. combined view (Q-030). |  | Relates to S-028, S-003.
Note on A1: Cypress Coverage / Command values: Not built yet / Manual review only / Future automation target / Needs technical review. Cypress Closure Status values: Open / Not Started / Needs Clarification / Confirmed / Future Phase / Ready for Review.

## Raw Notes
Date | Source | Notes | Related Area | Follow-Up Needed
2026-07-20 | Client message (chat) | Client described the app concept end to end: on open (Android or Apple), the app shows a branded "National Proficiency" animation, then a username/password login. After login it opens to the user's individual page with their photo on top, current rank, any medals achieved, and info on where to go next to achieve their next accomplishment. Selecting the Home page shows updates, monthly challenges, and possibly a community aspect. A second tab, next to Home, is a messaging/community-style communications section where people can keep each other updated on information or activities. | App overview -- Onboarding / Login / Profile / Home / Messaging | Broken into S-001 through S-005 (scope items) and Q-001 through Q-007 (open questions). Awaiting rank/medal system, account provisioning, monthly-challenge mechanics, and Home-vs-Messaging community clarification.
2026-07-20 | Client message (chat) | Client added: a Media tab after Home/Chat/Profile, premium-subscribers only, hosting medical training videos, fitness training videos, and firearms & building training videos (exact meaning of "building" unconfirmed). Whole app requires an account -- no guest access; new users create an account. Three tiers: Free (app + profile + Home, no chats/media/challenges), Mid ("being worked on" -- not yet defined by client), Premium (all features + monthly raffles tied to challenges + media + chats + additional personalized guidance based on what the user is working on). | App overview -- Media tab / Membership tiers / Paywall | Broken into S-006, S-007 (scope items), Q-008 through Q-013 (open questions), and R-001, R-002 (risks). Flagged: challenges were placed on Home (S-004) but Free tier excludes challenges -- gating logic within Home needs clarification (Q-011). Flagged: raffle tied to paid tier may have legal/compliance exposure (R-001).
2026-07-20 | Client message (chat) | Client confirmed National Proficiency and Tactical Rabbi are completely separate brands/companies, not associated, with no crossover of information between the two projects. | App overview -- Business context | Resolved the Tactical Rabbi sub-question inside Q-001 (closed). Core Q-001 business-description/audience question remains open. Flagged a repo-hygiene question to the client: both projects currently live in the same git repository -- asked whether National Proficiency's docs should move to a separate repo to guarantee no crossover. Client chose to move to a separate repo; blocked on the client creating an empty GitHub repo, since this session's GitHub integration cannot create new repositories (403 permission error).
2026-07-20 | Client message (chat) | Client described the instructor/backend side: Approved Instructors share the regular user's profile and access, plus a center-bottom "+" button opening a form to pre-register a student for a qualification -- category (Medical / Firearms / Fitness), level/tier, and date. Submission produces approval information and a Google Calendar attachment sent to the student. On qualification day (firearms example given), the instructor accesses that tier's shooting qualification standard/course of fire, and can record drill times via a "Shooter's Global" shot timer integration or type results in manually. All qualifications are strictly pass/fail, no leniency; any edit to recorded results must leave a verifiable record that an edit was made. After the instructor checks off each qualification item to standard, a Pass button updates the student's profile with the new medal/badge/accomplishment. | Instructor / backend -- Registration, qualification standards, grading | Broken into S-008 through S-013 (scope items), Q-014 through Q-018 (open questions), and R-003 (risk: qualification record-keeping/compliance). Confirms the earning mechanism behind S-003's rank/medal display and partially answers Q-001 (three pillars = Medical, Firearms, Fitness). Updated Q-002/Q-003 to note the mechanism is known but the actual standards content is still needed from the client.
2026-07-20 | Client message (chat) | Client described the role hierarchy and account/legal model: two cofounders have full access to edit any instructor or student record. Instructors register on a website, choose a specialty (Firearms/Fitness/Medical), and are individually vetted before being listed as Approved Instructors; a zip-code-based map lets users find nearby instructors for the drills they need. Instructors can upgrade a student's tier on qualification completion but cannot lower/remove a tier directly -- only submit a downgrade request with a required reason. New users create an account with basic info and are issued a unique serial number/code to access their account. Instructors sign a waiver to follow National Proficiency's standards; every user signs a liability waiver stating National Proficiency is solely a records-keeping company with no responsibility for shooting/medical/fitness outcomes -- liability and legal compliance rest with the individual. Separately, on the Media tab: users can earn digital badges by watching a specific video and passing an online quiz (e.g. a "How to Build an AR-15" video); the client also mentioned, more tentatively, additional leaderboard-style badges to rank against peers for camaraderie. | Instructor / backend -- Role hierarchy, vetting, waivers, locator map, media badges | Broken into S-014 through S-020 (scope items), F-001 (future idea -- leaderboard badges, described tentatively), and Q-019 through Q-024 (open questions). This substantially answers Q-001's business-model question (records-keeping only, no liability for outcomes) -- downgraded Q-001 from P0 to P2 since only the specific target market remains unstated. Also partially mitigates R-002/R-003 via the liability waiver, though enforceability still needs legal review.
2026-07-20 | Client message (chat) | Client clarified the instructor approval process could be done within the app itself for vetting (possible tension with the earlier "register on the website" statement -- not yet reconciled). Client also wants: (1) a Home tab leaderboard for Fitness and Firearms -- most badges earned, fastest mile, longest distance, and similar metrics; (2) integration allowing users to connect a Garmin, Apple Watch, or Strava account (their choice) to post/sync personal activity data, which could later support virtual qualifications tied to specific events. Client confirmed a full document with all qualifications and training information exists and will be provided on a later date. | Instructor vetting / Home leaderboard / Wearable integration / Standards document | Added S-021 (leaderboard, supersedes the more tentative F-001), S-022 (wearable integration), F-002 (future idea: virtual qualifications), and R-004 (risk: virtual-qualification data falsification). Updated Q-019/S-015 to flag the unreconciled website-vs-in-app vetting statements. Updated Q-002/Q-003/S-011 to note the qualifications/training document is confirmed to exist and is forthcoming -- the single biggest content gap now has a committed source, just not yet a date.
2026-07-20 | Client message (chat) | Client wants ID verification integrated into instructor and student registration -- via a third-party service (mentioned "ID.me" or similar) to confirm someone is over 18 and legally allowed to own a firearm, explicitly without National Proficiency storing sensitive ID/legal documents on its own systems. This also enables ban enforcement: if a banned person tries to re-register with new information, the system should recognize their previously verified identity and prevent it. | Registration -- ID verification, ban enforcement | Added S-023 (ID verification) and S-024 (ban enforcement via identity match). Added Q-025 through Q-028 and R-005 (P0 risk: standard ID-verification vendors typically confirm identity/age, not firearm-purchase eligibility, which usually needs a separate NICS-style background check -- flagged so the client doesn't assume more legal coverage than the vendor actually provides). Cross-referenced S-002, S-015, S-019 since this plugs into the existing registration flows for both instructors and students.
2026-07-20 | Client message (chat) | Client corrected the registration flow: instead of an instructor typing in a student's info and tier, the student now initiates from their own profile ("Register"/"Choose qualification day"), picks a category (Fitness, Medical, or Firearms), and the app -- already knowing their current tier -- only allows registering for the next eligible tier, then recommends nearby instructors. Instructors can only see qualification data for the specific course a student is actively registering for, not browse other tiers freely. Medical and Fitness standards are fully public (each tops out at a ceiling level); Firearms exact drills are hidden, but each tier shows the general skills needed to prepare. On the profile, in addition to photo and current rank, client wants a Pokemon-style progression visual: earned tiers/medals in full color, the in-progress tier grayed out, and future tiers blacked-out/locked as a preview. | Registration flow correction / Content visibility / Profile progression visual | Marked S-009 (old instructor-initiated registration) as Removed, superseded by new S-025 (student-initiated registration with auto-eligibility and instructor recommendation). Updated S-008 to remove the "+" button reference. Added S-026 (scoped instructor access to standards) and S-028 (profile progression visual). Updated S-011 and S-017 to reflect the new content-visibility rules and the overlap with the recommendation engine. Added Q-029 (unclear/possibly garbled instructor-visibility phrasing -- flagged rather than guessed), Q-030, Q-031.
Note on A1: Dump raw/messy input here first (meeting notes, screenshots described in text, client messages, brainstorming). Anything unclear should be promoted into Scope Items as a Q-### row.